## Jira Import
Issue Type | Epic Name | Epic Link | Summary | Assignee | Priority | Status | Original Estimate (hrs) | Labels | Description
Epic | Discovery & Planning |  | Discovery & Planning | Product/PM | High | To Do |  | docrenew
Epic | Requirements & UX Design |  | Requirements & UX Design | Product/PM | High | To Do |  | docrenew
Epic | Architecture & Tech Setup |  | Architecture & Tech Setup | Backend Dev | High | To Do |  | docrenew
Epic | Backend Development |  | Backend Development | Backend Dev | High | To Do |  | docrenew
Epic | Notifications & Integrations |  | Notifications & Integrations | Backend Dev | High | To Do |  | docrenew
Epic | Web Frontend Development |  | Web Frontend Development | Frontend Dev | High | To Do |  | docrenew
Epic | Mobile App Development |  | Mobile App Development | Mobile Dev | High | To Do |  | docrenew
Epic | QA & Testing |  | QA & Testing | QA | High | To Do |  | docrenew
Epic | Security & Compliance |  | Security & Compliance | Backend Dev | High | To Do |  | docrenew
Epic | Deployment & DevOps |  | Deployment & DevOps | DevOps | High | To Do |  | docrenew
Epic | Documentation & Training |  | Documentation & Training | Product/PM | High | To Do |  | docrenew
Epic | Launch & Go-to-Market |  | Launch & Go-to-Market | Product/PM | High | To Do |  | docrenew
Epic | Post-Launch |  | Post-Launch | Product/PM | High | To Do |  | docrenew
Task |  | Discovery & Planning | [T01] Stakeholder kickoff & goal alignment | Product/PM | High | In Progress | 4 | docrenew
Task |  | Discovery & Planning | [T02] Draft & approve Business Requirements Document (BRD) | Product/PM | High | Done | 2 | docrenew
Task |  | Discovery & Planning | [T03] Define success metrics & KPIs | Product/PM | Medium | Done | 1 | docrenew
Task |  | Discovery & Planning | [T04] Competitive landscape review | Product/PM | Low | Done | 1 | docrenew
Task |  | Discovery & Planning | [T05] Define pricing & packaging model | Product/PM | Medium | Done | 2 | docrenew
Task |  | Requirements & UX Design | [T06] Finalize functional requirements sign-off | Product/PM | High | To Do | 3 | docrenew
Task |  | Requirements & UX Design | [T07] Data model design (employee, document, reminder, org) | Backend Dev | High | Done | 2 | docrenew
Task |  | Requirements & UX Design | [T08] Notification & escalation workflow design | Product/PM | High | Done | 2 | docrenew
Task |  | Requirements & UX Design | [T09] Role & permission matrix (Admin/HR/Manager/Employee) | UX/Design | Medium | Done | 1 | docrenew
Task |  | Requirements & UX Design | [T10] Wireframes: dashboard, document repository, profile | UX/Design | High | Done | 4 | docrenew
Task |  | Requirements & UX Design | [T11] UI style guide / design system | UX/Design | Medium | Done | 2 | docrenew
Task |  | Requirements & UX Design | [T12] Mobile app UX flows | UX/Design | Medium | Done | 2 | docrenew
Task |  | Architecture & Tech Setup | [T13] Choose tech stack (web, mobile, backend, DB) | Backend Dev | High | Done | 2 | docrenew
Task |  | Architecture & Tech Setup | [T14] Cloud infrastructure setup (hosting, DB, storage) | DevOps | High | To Do | 5 | docrenew
Task |  | Architecture & Tech Setup | [T15] Repository & branching strategy setup | DevOps | Medium | Done | 1 | docrenew
Task |  | Architecture & Tech Setup | [T16] CI/CD pipeline setup | DevOps | Medium | Done | 3 | docrenew
Task |  | Architecture & Tech Setup | [T17] Dev / staging / production environments | DevOps | High | In Progress | 4 | docrenew
Task |  | Architecture & Tech Setup | [T18] Security architecture (encryption, RBAC design) | Backend Dev | High | Done | 3 | docrenew
Task |  | Backend Development | [T19] Authentication & role-based access control | Backend Dev | High | Done | 5 | docrenew
Task |  | Backend Development | [T20] Employee & document CRUD APIs | Backend Dev | High | Done | 6 | docrenew
Task |  | Backend Development | [T21] Secure document repository & encrypted storage | Backend Dev | High | Done | 5 | docrenew
Task |  | Backend Development | [T22] Reminder scheduling engine (3mo / 1mo / 5-day / expiry) | Backend Dev | High | Done | 8 | docrenew
Task |  | Backend Development | [T23] Escalation-to-management logic | Backend Dev | High | Done | 3 | docrenew
Task |  | Backend Development | [T24] Notification dispatch service (queue & retries) | Backend Dev | High | Done | 5 | docrenew
Task |  | Backend Development | [T25] Compliance & audit reporting APIs | Backend Dev | Medium | Done | 3 | docrenew
Task |  | Backend Development | [T26] Admin configuration APIs (reminder rules, org settings) | Backend Dev | Medium | Done | 3 | docrenew
Task |  | Notifications & Integrations | [T27] Email delivery integration (transactional provider) | Backend Dev | High | To Do | 4 | docrenew
Task |  | Notifications & Integrations | [T28] SMS gateway integration | Backend Dev | High | To Do | 4 | docrenew
Task |  | Notifications & Integrations | [T29] Push notification service integration | Backend Dev | Medium | To Do | 6 | docrenew
Task |  | Notifications & Integrations | [T30] Notification templates (email / SMS / push copy) | Product/PM | Medium | To Do | 2 | docrenew
Task |  | Web Frontend Development | [T31] Live compliance dashboard UI | Frontend Dev | High | Done | 6 | docrenew
Task |  | Web Frontend Development | [T32] Document management UI (upload, edit, view) | Frontend Dev | High | Done | 5 | docrenew
Task |  | Web Frontend Development | [T33] Employee profile UI | Frontend Dev | Medium | Done | 2 | docrenew
Task |  | Web Frontend Development | [T34] Admin/config UI (reminder rules, roles) | Frontend Dev | Medium | Done | 4 | docrenew
Task |  | Web Frontend Development | [T35] Reports & compliance export UI | Frontend Dev | Medium | To Do | 3 | docrenew
Task |  | Web Frontend Development | [T36] Role-based views (Admin/HR/Manager/Employee) | Frontend Dev | High | To Do | 4 | docrenew
Task |  | Mobile App Development | [T37] Mobile app scaffolding (iOS & Android) | Mobile Dev | High | To Do | 6 | docrenew
Task |  | Mobile App Development | [T38] Employee mobile views (my documents, alerts) | Mobile Dev | High | To Do | 5 | docrenew
Task |  | Mobile App Development | [T39] HR/Manager mobile views | Mobile Dev | Medium | To Do | 5 | docrenew
Task |  | Mobile App Development | [T40] Push notification wiring on mobile | Mobile Dev | Medium | To Do | 3 | docrenew
Task |  | Mobile App Development | [T41] App Store / Play Store submission prep | Mobile Dev | Low | To Do | 3 | docrenew
Task |  | QA & Testing | [T42] Test plan & test case authoring | QA | High | To Do | 3 | docrenew
Task |  | QA & Testing | [T43] Unit & integration testing | QA | High | To Do | 7 | docrenew
Task |  | QA & Testing | [T44] Notification delivery testing (email/SMS/push) | QA | High | To Do | 3 | docrenew
Task |  | QA & Testing | [T45] User acceptance testing (UAT) with pilot org | QA | High | To Do | 7 | docrenew
Task |  | QA & Testing | [T46] Security & penetration testing | QA | High | To Do | 6 | docrenew
Task |  | QA & Testing | [T47] Load & performance testing | QA | Medium | To Do | 4 | docrenew
Task |  | Security & Compliance | [T48] Data encryption at rest & in transit review | Backend Dev | High | To Do | 4 | docrenew
Task |  | Security & Compliance | [T49] Access control & permissions audit | Backend Dev | High | To Do | 4 | docrenew
Task |  | Security & Compliance | [T50] Data privacy / regulatory compliance review | HR/Compliance | High | To Do | 6 | docrenew
Task |  | Security & Compliance | [T51] Compliance report validation with legal/HR | HR/Compliance | Medium | To Do | 4 | docrenew
Task |  | Deployment & DevOps | [T52] Staging deployment & smoke test | DevOps | High | To Do | 3 | docrenew
Task |  | Deployment & DevOps | [T53] Production deployment | DevOps | High | To Do | 3 | docrenew
Task |  | Deployment & DevOps | [T54] Monitoring & alerting setup | DevOps | Medium | To Do | 3 | docrenew
Task |  | Deployment & DevOps | [T55] Backup & disaster recovery plan | DevOps | Medium | To Do | 3 | docrenew
Task |  | Documentation & Training | [T56] End-user guide (Employee) | Product/PM | Medium | To Do | 1 | docrenew
Task |  | Documentation & Training | [T57] Admin/HR user guide | Product/PM | Medium | To Do | 1 | docrenew
Task |  | Documentation & Training | [T58] API documentation | Backend Dev | Low | Done | 1 | docrenew
Task |  | Documentation & Training | [T59] HR onboarding & training materials | HR/Compliance | Medium | To Do | 2 | docrenew
Task |  | Launch & Go-to-Market | [T60] Pilot customer onboarding | Product/PM | High | To Do | 8 | docrenew
Task |  | Launch & Go-to-Market | [T61] Marketing / pitch materials finalized | Product/PM | Low | Done | 2 | docrenew
Task |  | Launch & Go-to-Market | [T62] Launch communication plan | Product/PM | Medium | To Do | 3 | docrenew
Task |  | Launch & Go-to-Market | [T63] Feedback collection & issue triage process | Product/PM | Medium | To Do | 3 | docrenew
Task |  | Post-Launch | [T64] Monitor KPIs (missed renewals, HR effort reduction) | Product/PM | High | To Do | 4 | docrenew
Task |  | Post-Launch | [T65] Customer support process | Product/PM | Medium | To Do | 4 | docrenew
Task |  | Post-Launch | [T66] Phase 2 roadmap (HRIS integrations, offline mobile) | Product/PM | Low | To Do | 2 | docrenew
Task |  | Requirements & UX Design | [T67] Extended item UX flows (Warranty, Vehicle Maintenance, Bill, AMC, Other Notifications) | UX/Design | High | Done | 3 | docrenew
Task |  | Backend Development | [T68] Extended item data model & category support (document_types.category, documents.item_label) | Backend Dev | High | Done | 3 | docrenew
Task |  | Backend Development | [T69] Extended item CRUD APIs & validation (non-employee-owned items) | Backend Dev | High | To Do | 4 | docrenew
Task |  | Web Frontend Development | [T70] Admin: extended item type management UI | Frontend Dev | High | To Do | 3 | docrenew
Task |  | Web Frontend Development | [T71] Dashboard/table & filters for extended item categories | Frontend Dev | Medium | To Do | 2 | docrenew
Task |  | QA & Testing | [T72] Regression testing for extended item categories | QA | High | To Do | 3 | docrenew
Task |  | Documentation & Training | [T73] Update BRD/FSD/schema docs for extended item categories | Product/PM | Medium | Done | 2 | docrenew
Total estimated effort
Notes:
- Estimates assume the entire build is done using Claude: coding, API scaffolding, UI implementation, and documentation hours are cut roughly 65-75% versus a fully manual build. Hours that depend on real people or real-world waiting — stakeholder meetings, legal/compliance review, cloud provisioning, UAT with live users, app store review — are reduced less, since AI assistance doesn't compress those.
- Import into Jira via Settings > System > External System Import > CSV. Map "Epic Name" rows first (or pre-create the 13 epics), then import the Task rows with "Epic Link" matching each Epic Name exactly.
- "Original Estimate (hrs)" is a planning-level estimate per task; Jira's CSV importer accepts this as a number of hours when mapped to the Original Estimate field (confirm your instance's time-tracking format: hours vs. "3d 4h" style).
- Status values (To Do / In Progress / Done) assume a default Jira workflow; rename to match your project's workflow if it differs.
- Priority and Assignee are placeholders reflecting current plan ownership — reassign to real Jira usernames before import.